## OQC Schedule(PA)
Item | Task list | L/T (Days) | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8 | Day9 | Day10 | Day11 | Day12 | Day13 | Day14 | Day15 | Day16 | Day17 | Day18 | Day19 | Day20 | Day21 | Day22 | Day23
1 | DUT Design lock (MCO, Gerber, 3D drawing, Schematic, Testplan)
2 | ME-Fixture Frame | 14 | bar: Day1 to Day16
2.1 | 3D Design | 4 | bar: Day1 to Day3
2.2 | 3D design review | 1 | bar: Day4
2.3 | 2D Drawing prepare | 1 | bar: Day5
2.4 | 2D drawing review&release | 1 | bar: Day6
2.5 | BOM Release | 1 | bar: Day6
2.6 | Standard Parts Ready | 14 | bar: Day3 to Day16
2.7 | Machining Parts Ready | 10 | bar: Day7 to Day16
3 | EE-Function boards | 15 | bar: Day1 to Day18
3.1 | Schematic design | 3 | bar: Day1 to Day3
3.2 | Schematic review | 1 | bar: Day4
3.3 | BOM Release | 1 | bar: Day5
3.4 | Material Ready | 10 | bar: Day5 to Day14
3.5 | PCB Layout Ready | 3 | bar: Day5 to Day7
3.6 | PCB Fabrication | 7 | bar: Day8 to Day14
3.7 | PCBA Ready | 2 | bar: Day15 to Day16
3.8 | PCBA Debug&calibration | 3 | bar: Day17 to Day18
4 | Assy.&Shipping | 8 | bar: Day17 to Day23
4.1 | Fixture Assembly | 3 | bar: Day17 to Day19
4.2 | Motion check, Blue film and aging test | 1 | bar: Day20
4.3 | Fixture System calibration and function OQC | 3 | bar: Day21 to Day22
4.4 | Fixture OQC&Shipping | 1 | bar: Day23

## EE Status(EE)
Project PCBA Status
NO. | Board Name | Version | Fixture Qty | New PO | Re-Work | PCB layout | BOM | Materials Delivery | PCB | PCBA | Materials Numbers | PCB Numbers | PCBA PASS | Status | Part Number
1 | IA868 Translation board | A4.22 | 2 | 10 | 24 | 2018-04-04 | 2018-04-04 | 2018-04-11 | 2018-04-12 | 2018-04-14 | 42 | 40 | 40 | 外发贴片中 | 103PP-01960IA.01
2 | USBC stick module | A3.3 | 4 | 20 | / | / | 2018-03-27 | 2018-04-07 | 2018-03-27 | 2018-04-09 | 40 | 50 |  | 贴片完成 | 103PP-01415IA.01
3 | IA868 USB3.0 Flex | A2.0 | 2 | 10 | / | [7 empty] | 14 | PCBA库存 | 103PP-30191IA.01
4 | USBC_Flex_IA | A4.0 | 4 | 20 | / | [7 empty] | 68 | PCBA库存 | 103PP-01346IA.01
5 | IA320 Audio board | A1.3 | 2 | 10 | / | / | 2018-03-27 | 2018-04-07 | 2018-03-27 | 2018-04-09 | 20 | 30 | 6 | 贴片完成 | 103PP-01295IA.01
6 | IA320 Digital board | A1.0 | 2 | 10 | / | [7 empty] | 17 | PCBA库存 | 103PP-00697IA.01
7 | Sensor_translation | A4.0 | 4 | 20 | 48 | 2018-03-28 | 2018-03-28 | 2018-04-07 | 2018-04-07 | 2018-04-09 | 100 | 100 | 100 | 贴片完成 | 103PP-01580IA.01
8 | IA860 6_led board A03 | A03 | 1 | 5 | / | [7 empty] | 33 | PCBA库存 | 103PP-01008IA.01
9 | IA_TCON_Interface_Board A1.0 | A1.0 | 2 | 10 | / | [7 empty] | 15 | PCBA库存 | 103PP-30228IA.01
10 | fixture Control board | V2.0 | 1 | 5 | / | 2018-03-28 | 2018-03-28 | 2018-04-10 | 2018-04-07 | 2018-04-12 | 10 | 20 | 10 | 贴片完成 | 103PP-01289IA.01
11 | Fixture interface board V1.1 | V1.1 | 1 | 5 | / | [7 empty] | 15 | PCBA库存 | 103PP-01057IA.01
16 | IA868 control interface board A1.0 | A1.0 | 1 | 5 | / | [7 empty] | 28 | PCBA库存 | 103PP-01239IA.01
12 | sensor interface board V1.1 | V1.1 | 1 | 5 | / | [7 empty] | 40 | PCBA库存 | 103PP-01058IA.01
13 | E_LOAD 4UP | A6.1 | 2 | 10 | / | 2018-03-28 | / | / | / | 2018-04-03 | / | / | 10 | 精实 | 103PP-00008CE.01
14 | IA320 Power Bridge board | A1.0 | 1 | 5 | / | 2018-03-28 | / | / | / | 2018-04-03 | / | / | 5 | 精实 | 103PP-00011CE.01
15 | IA Channel Board | A6.2 | 4 | 20 | / | 2018-03-28 | / | / | / | 2018-04-03 | / | / | 20 | 精实 | 103PP-00009CE.01
16 | Battery Emulation Board V2(SE2400-BE01-02) | (SE2400-BE01-02) | 2 | 10 | 24 | 2018-03-28 | / | / | / | 2018-04-13 | / | / | 10 | 广州 | 221AA-00001CB.01
17 | Test Base Board | SE2300-2-CM01PC-B | 2 | 10 | / | 2018-03-28 | / | / | / | 2018-04-13 | / | / | 10 | 广州 | 103PP-00123CB.01
18 | DMM Board | SE2300-AD01PC-A | 2 | 10 | / | 2018-03-28 | / | / | / | 2018-04-13 | / | / | 10 | 广州 | 05A1655305.001
19 | Data logger board | SE2300-AD03PC-A | 2 | 10 | / | 2018-03-28 | / | / | / | 2018-04-13 | / | / | 10 | 广州 | 05A1710404.001
20 | Power Sequence Board | SE2300-PS01PC-B | 2 | 10 | / | 2018-03-28 | / | / | / | 2018-04-13 | / | / | 10 | 广州 | 05A1710405.001
21 | ZYNQ(ARM) Board | SE2625-MU01PC-E | 2 | 10 | / | 2018-03-28 | / | / | / | 2018-04-13 | / | / | 10 | 广州 | 103PP-00082CB.01
22 | Digitizer Board | SE2300-AD02PC-A | 2 | 10 | / | 2018-03-28 | / | / | / | 2018-04-13 | / | / | 10 | 广州 | 103PP-00127CB.01
23 | Codec Board | SE2124-AU01PC-A | 2 | 10 | / | 2018-03-28 | / | / | / | 2018-04-13 | / | / | 10 | 广州 | 103PP-00150CB.01
24 | HWTE Mikey Board | Rev04 | 2 | 10 | / | 2018-03-28 | / | / | / | 2018-04-13 | / | / | 10 | 信恳智能 | T100AA-00953-0.01
25 | Potassium SMT | BAPR41/APN939-03791 | 2 | 10 | / | [7 empty] | 34 | 伊派克 | T100AA-00958-0.01
26 | IA868_F Emulation Board U | A4.0 | Debug |  |  | 2018-04-08 | 2018-04-08 | 2018-04-11 | 2018-04-12 | 2018-04-13 | 10 | 10 | 10 | 外发贴片中 | 103PP-01929IA.01
27 | IA868_F Emulation Board_D | A4.0 | Debug |  |  | 2018-04-04 | 2018-04-04 | 2018-04-10 | 2018-04-10 | 2018-04-13 |  |  |  | 完成
29 | IA868_Dummy_DUT DVT | A1.0 | Debug |  |  | 2018-04-04 | / | / | 2018-04-13 | / | / | / | / |  | 101PA-05214IA.01
31 | Usb_Debug_Port_Board | A4.0 | Debug |  |  | 2018-04-08 | 2018-04-08 | 2018-04-13 | 2018-04-13 | 2018-04-14 |  |  |  |  | 103PP-01235IA.01

## Fixture OQC Status(DRI)
Onging | Need follow up by days | SS Engineer | XXX.XXX
Closed | Finished | PA | xxxx
OPEN | Need follow up by hours | QE | xxxx
IAxxx P1 Fixture OQC Bring Up Status
Fixture-ID | Items | Assembly(组装) | Action Check(动作调试) |  |  |  | System Test(系统调试) |  |  | Packaging(打包)
| Process | Fixture Assembly | Sensor Check | Action Check | Blue Tape | Burn-In | Module Test | System Function Test | System Calibration | Shipping Report Check | Spare Part Check | OQC Status
| DRI | PA xxx | QE xxx | QE xxx | QE xxx | QE xxx | SS XXX | SS XXX | SS XXX | SS XXX | QE xxx | QE xxx
IAXXX-FCT-P1-V01.00-001 | 20180401: XX module assembly delay. 20180402: Debug Ongoing. | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
IAXXX-FCT-P1-V01.00-002 | 20180401:Standard Moudle delay. 20180401-19:20: Module delay. | 2018-04-02 | 1900-01-03 04:48 | 1900-01-03 04:48 | 1900-01-03 04:48 | 1900-01-03 04:48 | 1900-01-03 04:48 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
IAXXX-FCT-P1-RACK-V01.00-002 |  | 2018-04-02 | 2018-04-02 | 2018-04-02 | NA | 2018-04-02 | NA | 2018-04-02 | NA | 2018-04-02 | 2018-04-02 | 2018-04-02
Fixture ID | Blue Tape Report | Hardware Version List | Module Test Report | System Test Coverage | Calibration Report | OQC Report | Summary | Target Date | Owner | Remark
IAXXX-FCT-P1-V01.00-001 | 4.2 | 4.2 | 4.2 | 4.2 | 4.2 | 4.2 | FAIL | 20180403 | xxx | Waiting DCR fixture release.
IAXXX-FCT-P1-V01.00-002 | 4.2 | 4.2 | 4.2 | 4.2 | 4.2 | 4.2 | FAIL | 20180403 | xxx | Waiting DCR fixture release.
IAXXX-FCT-P1-V01.00-003 | 4.2 | 4.2 | 4.2 | 4.2 | 4.2 | 4.2 | PASS | 20180403 | xxx
IAXXX-FCT-P1-RACK-V01.00-002 | 4.2 | 4.2 | 4.2 | 4.2 | 4.2 | 4.2 | PASS | 20180403 | xxx

## Fixture Bring Up Issue Tracking
High risks/off track
Low risk/on track
No risk/Done
Item | Project | Type | Priority | Station | Design Stage | Report Date | Issue Description | Pictures | Root Cause | Short term solution | Long term solution | DRI | ETA | Radar | Remark
1 | IAXXX | EE | SKIP | FCT | P1 Dry Run | 2018-01-23 | Need change speaker LOAD circuit. |  | New design | Need change speaker load resistor from 4Ohm to 8Ohm. | Need change speaker load resistor from 4Ohm to 8Ohm. | Peter.yang | 2018-03-03
2 | IAXXX | SE | SKIP | FCT | P1 Dry Run | 2018-01-27 | WIFI and BT command return error. Still not work. |  | x86 execute “pci 1 0 0 -s 0” command issue. It return timt out error then fail to perform operation. | Waiting for new command | Waiting for new command | NAPA |  | 36954440 | 1, Waiting for verify this command. 20180127 2, Log have sent to Radar. 20180129 3, Change boot MAC EFI command to : x86 boot --bootstate otheros. Still not work. Manual check this command, the issue happen is the same as run sequence. 20180130 4, Try to send command at MAC EFI side, the command is working but DUT still not power on WF/BT. Waiting for NAPA help to check this command. 20180201 5, Use pci 3 0 0 -s 0 command instead of the old command. This command can get WIFI/BT present data from DUT response.But still can’t output any power rails for WIFI/BT. 20180202 6, DUT power rail test point is under the DUT package. Can’t measure them. 20180205
3 | IAXXX | SE | SKIP | FCT | P1 Dry Run | 2018-01-29 | Speaker command return error and not found path. “spk/spkl/spl1”. |  | Command issue | Need diags team help to check speaker command. | Need diags team help to check speaker command. | NAPA | SKIP | 36913289 | 1, Waiting new command. 20180125 2, Skip at dry run, and will be tested at P1 build. 20180126
4 | IAXXX | SE |  | FCT | P1 Dry Run | 2018-02-14 | Can’t load profile when change test-plan name or comment. |  | Comment issue | Change comment. | Test-plan name format[20180207-171330__AP2.12.6_IA1.0.0]. Also the please more careful for the “,” when using sublime to edit test-plan. | ALL
5 | IAXXX | SE |  | FCT | P1 Dry Run | 2018-02-15 | Potassium disconnect causing test fail or engine timeout. |  | Test-plan control potassium by the wrong test sequence. | The engine.log/flow.log/iefi.log can debug this issue. | Do the right test sequence when disconnect or connect potassium before send or receive data from DUT. | Ray.huang |  |  | 1, Received updated test-plan from David and check test sequence. 20180224
10 | IAXXX | ME |  | FCT | P1 Build | 2018-03-05 | We found it is hard to put the fixture into the second floor of rack. |  | The fixture is 3up and rack is very big, caused sheet metal under key and mouse tray out of shape, so the fixture is hard to fit in. | Re-do fixture bracket of rack and change the drilling location to increase the height of 2nd floor. | Reduce the height of key and mouse tray to increase the height of 2nd floor. | Zhaohui.Zeng | 2018-03-07
11 | IAXXX | SW |  | FCT | P1 Build | 2018-03-07 | 1pcs DUT fail in Mini build at MAC EFI CMD TEST/PRINT_MAESTRE_EFI, log shows:timed out waiting for response from test engine in test. |  | Under verification. | Under verification. | Under verification. | Kyle.Yan | 2018-03-07 |  | 0308:Change the function and loop test 200x, no similar issue found.
12 | IAXXX | ME |  | FCT | P1 Build | 2018-03-08 | DMM SOC_DFU_STATUS; limits:{'high_limit': '1.9', 'low_limit': ‘1.7’}, actual:0.024 |  | We think the DUT did not enter DFU mode caused the issue. Suspect the support plate a little warping caused slot 2 probe contact issue. | 1.We redid blue tape with our blue tape board and figured out probe of SOC_DFU_STATUS test point can be contacted well. 2.Added SOC_FORCE_DFU measurement in test plan and checked the voltage output 1.8V, the SOC_DFU_STATUS can output voltage 1.8V. | Under verification. | Kyle.Yan/Zhaohui.Zeng | 2018-03-09 |  | 0309:In and out loop test 20 times on this fixture, no similar issue found, will continue loop test and keep monitoring. 0310:Keep on in and out loop test 20 times on this fixture, no similar issue found, still continue loop test and keep monitoring. 0312:Keep on in and out loop test 10 times on this fixture, no similar issue found, still continue loop test and keep monitoring.