## Build Member List(PM)
IAXXX-FCT P1 Dry Run Member List
Role | Name | CHINESE NAME | Email Address | Badge ID | ETA Onsite
PM |  |  |  |  | 2018-01-23
EE |  |  |  |  | 2018-01-23
FAE |  |  |  |  | 2018-01-23
ME |  |  |  |  | 2018-01-23
SS

## Fixture Bring Up Tracker(PM)
IAXXX-FCT P1 Fixture Bring Up Tracker
SW Bundle Version: iOS Bundle: iEFI Version: EFI Version: IA OVL Version: 1.2.2 AP Python Version: 2.12.6
Update: 2018/03/10 D |  |  |  | Finished
Validation MLB: P1 Build |  |  |  | Ongoing
Delay
Fixture SN | Fixture Arrived Online | Slot Number | Set Up | Install PSU | Strain Gauge | Blue Tape | GND&ESD | Power On Check | Test Sequence Complete | Loop Test | Ready To Go | Remark
IAXXX-FCT-P1-V01.00-001 | 2018-02-24 | SLOT1 | 2018-02-24 | 2018-02-24 | 2018-02-27 | 2018-02-26 | 2018-02-26 | 2018-02-26 | 2018-03-04 | 2018-03-04 | 2018-03-05 | 20180402: xxxxx
|  | SLOT2 | 2018-02-24 | 2018-02-24 | 2018-02-27 | 2018-02-26 | 2018-02-26 | 2018-02-26 | 2018-03-04 | 2018-03-04 | 2018-03-05
|  | SLOT3 | 2018-02-24 | 2018-02-24 | 2018-02-27 | 2018-02-26 | 2018-02-26 | 2018-02-26 | 2018-03-04 | 2018-03-04
IAXXX-FCT-P1-V01.00-002 | 2018-02-24 | SLOT1 | 2018-02-24 | 2018-02-24 | 2018-02-27 | 2018-02-26 | 2018-02-26 | 2018-02-26 | 2018-03-04 | 2018-03-04 | 2018-03-05
|  | SLOT2 | 2018-02-24 | 2018-02-24 | 2018-02-27 | 2018-02-26 | 2018-02-26 | 2018-02-26 | 2018-03-04 | 2018-03-04 | 2018-03-05
|  | SLOT3 | 2018-02-24 | 2018-02-24 | 2018-02-27 | 2018-02-26 | 2018-02-26 | 2018-02-26 | 2018-03-04 | 2018-03-04 | 2018-03-05
IAXXX-FCT-P1-V01.00-003 | 2018-02-24 | SLOT1 | 2018-02-24 | 2018-02-24 | 2018-02-27 | 2018-02-24 | 2018-02-27 | 2018-02-27 | 2018-03-05 | 2018-03-05 | 2018-03-05
|  | SLOT2 | 2018-02-24 | 2018-02-24 | 2018-02-27 | 2018-02-24 | 2018-02-27 | 2018-02-27 | 2018-03-05 | 2018-03-05 | 2018-03-05
|  | SLOT3 | 2018-02-24 | 2018-02-24 | 2018-02-27 | 2018-02-24 | 2018-02-27 | 2018-02-27 | 2018-03-05 | 2018-03-05 | 2018-03-05
IAXXX-FCT-P1-V01.00-004 | 2018-02-24 | SLOT1 | 2018-02-24 | 2018-02-24 | 2018-02-27 | 2018-02-24 | 2018-02-28 | 2018-02-28 | 2018-03-05 | 2018-03-05 | 2018-03-05
|  | SLOT2 | 2018-02-24 | 2018-02-24 | 2018-02-27 | 2018-02-24 | 2018-02-28 | 2018-02-28 | 2018-03-05 | 2018-03-05 | 2018-03-05
|  | SLOT3 | 2018-02-24 | 2018-02-24 | 2018-02-27 | 2018-02-24 | 2018-02-28 | 2018-02-28 | 2018-03-05 | 2018-03-05 | 2018-03-05
IAXXX-FCT-P1-V01.00-005 | 2018-02-24 | SLOT1 | 2018-02-24 | 2018-02-24 | 2018-02-27 | 2018-02-26 | 2018-03-01 | 2018-03-01 | 2018-03-06 | 2018-03-06 | 2018-03-06
|  | SLOT2 | 2018-02-24 | 2018-02-24 | 2018-02-27 | 2018-02-26 | 2018-03-01 | 2018-03-01 | 2018-03-06 | 2018-03-06 | 2018-03-06
|  | SLOT3 | 2018-02-24 | 2018-02-24 | 2018-02-27 | 2018-02-26 | 2018-03-01 | 2018-03-01 | 2018-03-06 | 2018-03-06 | 2018-03-06
IAXXX-FCT-P1-V01.00-006 | 2018-02-24 | SLOT1 | 2018-02-24 | 2018-02-24 | 2018-02-27 | 2018-02-24 | 2018-03-01 | 2018-03-01 | 2018-03-06 | 2018-03-06 | 2018-03-06
|  | SLOT2 | 2018-02-24 | 2018-02-24 | 2018-02-27 | 2018-02-24 | 2018-03-01 | 2018-03-01 | 2018-03-06 | 2018-03-06 | 2018-03-06
|  | SLOT3 | 2018-02-24 | 2018-02-24 | 2018-02-27 | 2018-02-24 | 2018-03-01 | 2018-03-01 | 2018-03-06 | 2018-03-06 | 2018-03-06
IAXXX-FCT-P1-V01.00-007 | 2018-02-26 | SLOT1 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-03-01 | 2018-03-01 | 2018-03-07 | 2018-03-07 | 2018-03-07
|  | SLOT2 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-03-01 | 2018-03-01 | 2018-03-07 | 2018-03-07 | 2018-03-07
|  | SLOT3 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-03-01 | 2018-03-01 | 2018-03-07 | 2018-03-07 | 2018-03-07
IAXXX-FCT-P1-V01.00-008 | 2018-02-26 | SLOT1 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-03-01 | 2018-03-01 | 2018-03-07 | 2018-03-09 | 2018-03-10
|  | SLOT2 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-03-01 | 2018-03-01 | 2018-03-07 | 2018-03-09 | 2018-03-10
|  | SLOT3 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-03-01 | 2018-03-01 | 2018-03-07 | 2018-03-09 | 2018-03-10

## Fixture Bring Up Issue Tracking
High risks/off track
Low risk/on track
No risk/Done
Item | Project | Type | Priority | Station | Design Stage | Report Date | Issue Description | Pictures | Root Cause | Short term solution | Long term solution | DRI | ETA | Radar | Remark
1 | IAXXX | EE | SKIP | FCT | P1 Dry Run | 2018-01-23 | Need change speaker LOAD circuit. |  | New design | Need change speaker load resistor from 4Ohm to 8Ohm. | Need change speaker load resistor from 4Ohm to 8Ohm. | Peter.yang | 2018-03-03
2 | IAXXX | SE | SKIP | FCT | P1 Dry Run | 2018-01-27 | WIFI and BT command return error. Still not work. |  | x86 execute “pci 1 0 0 -s 0” command issue. It return timt out error then fail to perform operation. | Waiting for new command | Waiting for new command | NAPA |  | 36954440 | 1, Waiting for verify this command. 20180127 2, Log have sent to Radar. 20180129 3, Change boot MAC EFI command to : x86 boot --bootstate otheros. Still not work. Manual check this command, the issue happen is the same as run sequence. 20180130 4, Try to send command at MAC EFI side, the command is working but DUT still not power on WF/BT. Waiting for NAPA help to check this command. 20180201 5, Use pci 3 0 0 -s 0 command instead of the old command. This command can get WIFI/BT present data from DUT response.But still can’t output any power rails for WIFI/BT. 20180202 6, DUT power rail test point is under the DUT package. Can’t measure them. 20180205
3 | IAXXX | SE | SKIP | FCT | P1 Dry Run | 2018-01-29 | Speaker command return error and not found path. “spk/spkl/spl1”. |  | Command issue | Need diags team help to check speaker command. | Need diags team help to check speaker command. | NAPA | SKIP | 36913289 | 1, Waiting new command. 20180125 2, Skip at dry run, and will be tested at P1 build. 20180126
4 | IAXXX | SE |  | FCT | P1 Dry Run | 2018-02-14 | Can’t load profile when change test-plan name or comment. |  | Comment issue | Change comment. | Test-plan name format[20180207-171330__AP2.12.6_IA1.0.0]. Also the please more careful for the “,” when using sublime to edit test-plan. | ALL
5 | IAXXX | SE |  | FCT | P1 Dry Run | 2018-02-15 | Potassium disconnect causing test fail or engine timeout. |  | Test-plan control potassium by the wrong test sequence. | The engine.log/flow.log/iefi.log can debug this issue. | Do the right test sequence when disconnect or connect potassium before send or receive data from DUT. | Ray.huang |  |  | 1, Received updated test-plan from David and check test sequence. 20180224
6 | IAXXX | SE |  | FCT | P1 Dry Run | 2018-02-22 | Station timeout response comment”AMIOK ERROR: class 32, id:13. message: File is old.” |  | PDCA server config issue. | Wave this issue at US lab. Will keep look at this issue at FXCD. | Need re-config the PDCA server at US lab. | NAPA | SKIP
7 | IAXXX | SE |  | FCT | P1 Dry Run | 2018-02-22 | Receive new power off sequence. Need change test sequence. |  | Need change test sequence. |  | Need change test sequence. | Ray.huang |  |  | 1, Ongoing. Will update new test-plan to git later. Also need DUT to verify this test sequence.20180223
8 | IAXXX | EE |  | FCT | P1 Build | 2018-03-03 | We test PP12V_FAN_FILT is 12V under Macc IEFI, but change to 1.2V under Mac EFI status. |  | Need to verify. | Open the limit. | Continue to verify this issue. | Ray.huang/NAPA | 2018-03-04 |  | We have verified that after added “resetblock clifden,,,,, 2000, RESET AUDIO CLIFTEN” command, PP12V_FAN_FILT can output 12V under Mac EFI status.
9 | IAXXX | EE |  | FCT | P1 Build | 2018-03-03 | We measured speaker THDN frequency amplitude is 4V, suspect would be 2V. |  | We found out that the hardware is new design, so we need to change voltage divide resistor of software from 6.1V to 3V. | change voltage divide resistor of software from 6.1V to 3V. | change voltage divide resistor of software from 6.1V to 3V. | Ray.huang | 2018-03-04 | 2018-03-04
10 | IAXXX | ME |  | FCT | P1 Build | 2018-03-05 | We found it is hard to put the fixture into the second floor of rack. |  | The fixture is 3up and rack is very big, caused sheet metal under key and mouse tray out of shape, so the fixture is hard to fit in. | Re-do fixture bracket of rack and change the drilling location to increase the height of 2nd floor. | Reduce the height of key and mouse tray to increase the height of 2nd floor. | Zhaohui.Zeng | 2018-03-07
11 | IAXXX | SW |  | FCT | P1 Build | 2018-03-07 | 1pcs DUT fail in Mini build at MAC EFI CMD TEST/PRINT_MAESTRE_EFI, log shows:timed out waiting for response from test engine in test. |  | Under verification. | Under verification. | Under verification. | Kyle.Yan | 2018-03-07 |  | 0308:Change the function and loop test 200x, no similar issue found.
12 | IAXXX | ME |  | FCT | P1 Build | 2018-03-08 | DMM SOC_DFU_STATUS; limits:{'high_limit': '1.9', 'low_limit': ‘1.7’}, actual:0.024 |  | We think the DUT did not enter DFU mode caused the issue. Suspect the support plate a little warping caused slot 2 probe contact issue. | 1.We redid blue tape with our blue tape board and figured out probe of SOC_DFU_STATUS test point can be contacted well. 2.Added SOC_FORCE_DFU measurement in test plan and checked the voltage output 1.8V, the SOC_DFU_STATUS can output voltage 1.8V. | Under verification. | Kyle.Yan/Zhaohui.Zeng | 2018-03-09 |  | 0309:In and out loop test 20 times on this fixture, no similar issue found, will continue loop test and keep monitoring. 0310:Keep on in and out loop test 20 times on this fixture, no similar issue found, still continue loop test and keep monitoring. 0312:Keep on in and out loop test 10 times on this fixture, no similar issue found, still continue loop test and keep monitoring.
13 | IAXXX | EE |  | FCT | P1 Build | 2018-03-08 | Timed out waiting for response. |  | Suspect the communication issue between Mikey board and ZYNQ board. | 1.We used client software to communicate with Mikey board, but no response. 2.After reset ZYNQ board manually, the Mikey board communicate with the ZYNQ board well. | Under discussion. | Peter.Yang | 2018-03-09 |  | 0309:Under verification on IA site, will send the report after finish DOE.
14 | IAXXX | EE |  | FCT | P1 Build | 2018-03-08 | MAC EFI POWER RAIL GROUP::DMM PPVCC_S0_CPU_REG; limits:{'high_limit': '0.792', 'low_limit': '0.6'} |  | AAB fail, check the actual value is 0.866V. Sent to EE for verification. | AAB fail. | Pending for EE verification. | CM | 2018-03-09 |  | 0309:Update the limit to {high_limit:1.55, low_limit:0.55} on overlay version v1.1.8, keep monitoring. 0310:Update the limit to {high_limit:1.705, low_limit:0.495} on overlay version v1.2.0, keep monitoring.
15 | IAXXX | EE |  | FCT | P1 Build | 2018-03-12 | The support plate a little warping. |  | Because the long span of 3up fixture support plate. | Add suooprt block on each support plate of each fixture. | Optimize the 3up fixture design in next build, reduce the support plate size, reduce the hollow of support plate and increase the thickness of support plate to solve this issue. | Zhaohui.Zeng | 2018-03-13
16 | IAXXX | EE |  | FCT | P1 Build | 2018-03-17 | IEFI AUDIO MIKEY TONES/MIKEY BOARD CHINAMODE@MIK0018(Timed out waiting for response) |  | Under verification. | Under verification. | Under verification. | Kyle/Ray | 2018-03-19 |  | DOE1: Action1:We did 60 times loop test on fixture004/slot3 with 1pc sop board, the same issue happened twice. we swap Mikey board of slot2 and slot3 to do loop test on these two slot, keep monitor if the same issue will happen again. ——> The similar issue still happened at the slot3 after loop test 80 times.——0316 Action2:We swap the USB cable of slot2 and slot3 to do loop test on these two slot, after 200 times loop test, the similar issue happened on slot3. Action3:We swap the whole Testbase board including ZYNQ board of slot2 and slot3 to do loop test, loop test 200 times, the similar issue still happened on slot3.——3/20 DOE2: We are doing software burn in test to monitor the communication between Mikey board and ZYNQ board. ——> We found some times “timeout error running” happen during software burn in test, so we changed the command sending mode, loop sending instead of sending once until it succeed. Pending for the loop test result.——3/20 ——> We ran 200 times loop test on fixture 004, no same issue happen.——3/21
17 | IAXXX | EE |  | FCT | P1 Build | 2018-03-17 | Some of the points that DMM reads are abnormal. |  | Under verification. | Under verification. | Under verification. | Kyle/Zhaohui.zeng | 2018-03-19 |  | Action1:We inspect the TP under microscope, found there are twice test failure because test point covered by glue. Clean the test point and retest pass.——3/14 Action2:Did blue tape for TP with failure on the same fixture. Result is OK. DOE1: Loop test on FD fixture without test motion and repeatedly measure TP voltage and check the result;——>cut off 3/15 15:00, totally loop test 10 times per slot and repeatedly test IBOOT ACTIVE GROUP 10 times per loop, no similar issue found. DOE2: Loop test on FD fixture with test motion and measure TP voltage, check the result.——>loop test about 100 times, no similar issue found.Still keep loop test.——0317 DOE3: Suspect there is a little deformation on support plate of some fixtures caused pogo pins contact issue. As short term solution, we take out of the fixture 002 stop block of press plate to make the carrier plate fit well with pogo plate to ease the contact issue. ——>Fixture002 a.Before taking out of stop block: 3/12 8:00-3/16 20:00 retest rate is 4.55% b.After taking out of stop block: 3/16 20:00-3/19 18:00 retest rate is 0.98%. ——>Fixture005 a.Before taking out of stop block: 3/12 8:00-3/15 23:00 retest rate is 4.00% b.After taking out of stop block: 3/15 23:00-3/19 18:00 retest rate is 0.86%. ——>Fixture001 a.Before taking out of stop block: 3/12 8:00-3/17 14:00 retest rate is 4.27% b.After taking out of stop block: 3/17 14:00-3/19 18:00 retest rate is 1.27%.

## Test Coverage Bring Up Status
IAXXX FCT P1 Dry Run Bring up Process |  | Pass
Debugging
Blocker
Project | Station | Build
IAXXX | FCT | P1 Dry Run
Fixture Bring up Process | Bring Up Status
| Date | Remark
Drawer arrive Line | 2018-01-24 | PASS
Cosmetic/GDS/ESD Check | 2018-01-24 | PASS
Fixture Power on and Movement Check | 2018-01-25 | PASS
Test coverage bring up starts | 2018-01-25 | PASS
FIXTURE SETUP | 2018-01-25 | PASS
IBOOT POWER SEQUENCE GROUP | 2018-01-25 | PASS
IBOOT ACTIVE GROUP | 2018-01-25 | PASS
IEFI SOC GROUP | 2018-01-25 | PASS
IEFI CB SETUP | 2018-01-25 | PASS
MAC IEFI TEMP SENSOR GROUP | 2018-02-02 | TA0P, TI0D, TI0P, TI0d, TP2H command not work
IEFI POWER RAIL GROUP | 2018-01-25 | PASS
IEFI SMC READ GROUP | 2018-01-26 | PASS
IEFI SENSOR RAIL GROUP | 2018-01-29 | PASS
IEFI AUDIO MIKEY TONES GROUP | 2018-01-25 | PASS
IEFI AUDIO HEADSET GLOBAL RIGHT LOOPBACK | 2018-01-26 | PASS
IEFI AUDIO HEADSET GLOBAL LTOR XTALK | 2018-01-26 | PASS
IEFI AUDIO HEADSET GLOBAL LEFT LOOPBACK | 2018-01-26 | PASS
IEFI AUDIO HEADSET GLOBAL RTOL XTALK | 2018-01-26 | PASS
IEFI AUDIO HEADSET CHINA RIGHT LOOPBACK | 2018-01-26 | PASS
IEFI AUDIO HEADSET CHINA LTOR XTALK | 2018-01-26 | PASS
IEFI AUDIO HEADSET CHINA LEFT LOOPBACK | 2018-01-26 | PASS
IEFI AUDIO HEADSET CHINA RTOL XTALK | 2018-01-26 | PASS
IEFI AUDIO SPEAKER PRESENCE GROUP | 2018-01-25 | PASS
IEFI AUDIO SPEAKER GROUP | SKIP | DUT not support this function, P1 will continue verify.
IEFI FAN SETUP | 2018-01-25 | PASS
IEFI FAN LOW SPEED | 2018-01-25 | PASS
IEFI FAN HIGH SPEED | 2018-01-25 | PASS
IEFI FAN I2C TEST GROUP | 2018-01-29 | PASS
MAC EFI BOOT GROUP | 2018-01-27 | PASS
MAC EFI SMC ADC READ GROUP | 2018-01-29 | PASS
MAC EFI POWER SEQUENCE GROUP | 2018-01-27 | PASS
MAC EFI POWER RAIL GROUP | 2018-01-27 | PASS
MAC EFI WIFI/BT | SKIP | Power rail TP under the DUT package, can’t measure them.
MAC EFI USBA TEST SETUP | 2018-01-25 | PASS
USBA ELOAD SETUP GROUP | 2018-01-25 | PASS
USBA EXTA TEST GROUP | 2018-01-25 | PASS
USBA EXTB TEST GROUP | 2018-01-25 | PASS
MAC EFI USBC ELOAD SETUP | 2018-01-27 | PASS
MAC EFI USBC XA XB TOP ELOAD | 2018-01-31 | PASS
MAC EFI USBC XA XB BOTTOM ELOAD | 2018-01-31 | PASS
MAC EFI USBC TA TB TOP ELOAD | 2018-01-27 | PASS
MAC EFI USBC TA TB BOTTOM ELOAD | 2018-01-27 | PASS
MAC EFI EHTERNET GROUP | 2018-02-02 | Both 1GB and 10GB can work, Need verify the SF at FXCD.
INTEL PWR DOWN | 2018-01-31 | PASS
FINAL CB SETUP | 2018-01-25 | PASS
SOC PWR DOWN | 2018-01-25 | PASS
Loop Test | 2/5-2/8

## Main Build issue tracking list
Closed
in Progress, Low risk
Critical
Blocker
Item | Project | Station | Type | Priority | Report Date | Fixture/Slot | Issue Description | Fail/Retest | Total Input | Fail/Retest Rate | Status | Radar | Remark
1 | IAXXX | FCT | SW |  | 2018-03-07 | 002/slot3 | MAC EFI CMD TEST/PRINT_MAESTRE_EFI1 | 1 | 11 | 1R/11T RR: 9.09% | SN: C0781020009JRXN4B, Config: Mini 03 AA pass, Fixture/Slot: 2/3 1.Fail log showed: timed out waiting for response from test engine in test 2.Time out limit is not enough 3. Change the function and loop test 200x, no similar issue found | 38219477
2 | IAXXX | FCT | HW |  | 2018-03-08 | 004/slot3 | IEFI AUDIO MIKEY TONES/MIKEY BOARD CHINAMODE@MIK0018（Timed out waiting for response) | 4 | 13 | 1R/13T RR:7.69% | SN: C078102000CJJ3N23, Config: Mini 01, AAB pass, Fixture/Slot: 4/3SN: C078112000XJKL265, Config: Main 2-B-BTR, Fixture/Slot: 4/3SN: C078112002DJKL26H, Config: Main 2-B-BTR, Fixture/Slot: 4/3SN: C078115000SJRWL3W, Main 65-U CTO 1, Fixture/Slot: 3/1,AA pass1. The log shows: Timed out3. Totally found 3 same failures at Fixture/Slot 4/3, turn off this slot4. we did 60 times loop test on fixture004/slot3 with 1pc sop board, the same issue happened twice. we swap Mikey board of slot2 and slot3 to do loop test on these two slot, keep monitor if the same issue will happen again. ——> The similar issue still happened at the slot3 after loop test 80 times. ——> Swap the USB cable of slot2 and slot3 to do loop test on these two slot. After loop test 200 times per slot, the similar issue happened on slot3. ——>Swap the whole TestBase board including ZYNQ board of slot2 and slot3 to do loop test, loop test 200 times, the similar issue still happened at slot3.5.We found some times “timeout error running” happen during software burn in test, so we changed the command sending mode, loop sending instead of sending once until it succeed. Pending for the loop test result.——3/20 | 38257110
3 | IAXXX | FCT | HW |  | 2018-03-08 | 002/slot2 | SOC PWR GROUP/DMM SOC_DFU_STATUS(limits:{'high_limit': '1.9', 'low_limit': ‘1.7'} ,actual 0.024) | 9 | 13 | 1R/13T RR:7.69% | SN: C0781020005JJ3N2A, Config: Mini 01, AA pass, Fixture/Slot: 2/2SN: C0781120013JKLH6F, Config: Main15-B-CTO7, Fixture/Slot: 1/2, AA passSN: C078112000PJKLH6Y, Config: Main15-B-CTO7, Fixture/Slot: 1/3, AA passSN: C078115003TJRWL3L, Main 65-U CTO 1, Fixture/Slot: 1/1,AAB passSN: C078115000LJRWL32, Main 65-U CTO 1, Fixture/Slot: 1/1,AAB passSN: C0781150013JRG94Y, Fixture/Slot: 6/1, AA pass SN: C0781150013JRG94Y, Fixture/Slot: 6/1, AA passSN: C0781160031JRJG4E, Fixture/Slot: 6/2, AA pass1.Redid blue tape with blue tape board and figured out probe of SOC_DFU_STATUS test point can be contacted well. 2.Added SOC_FORCE_DFU measurement in test plan and checked the voltage output 1.8V, the SOC_DFU_STATUS can output voltage 1.8V.3.Suspect contact issue caused the DUT did not enter DFU mode4.In and out loop test 15 on this fixture, no similar issue found, keep monitor5. 3/16, add 2x retest6, 3/17, add 2x retest7, 3/18 add 2x retest8, 3/19, add 1x retest SN: C0781210001JRNQ38, Fixture/Slot: 6/2, AAB pass3/21, add 1x retest | 38257154
4 | IAXXX | FCT | HW |  | 2018-03-08 | 002/slot1 | MAC EFI POWER RAIL GROUP/DMM PPVCC_S0_CPU_REG (limits:{‘high_limit': '0.792', 'low_limit': ‘0.6’}, actual 0.866v | 1 | 13 | 1F/13T FR:7.69% | SN: C0781020008JJ3N27, Config: Mini 01AAB fail, Fixture/Slot: 2/11. Check the actual value is 0.866V. Sent to EE for verification.2. Update the limit to {high_limit:1.55, low_limit:0.55} on overlay version v1.1.8, keep monitor | 38256968
5 | IAXXX | FCT | HW |  | 2018-03-14 | 005/slot2 | MAC EFI ETHERNET GROUP/ETHERNET DMM PP0V85actual value is 0.0, {'high_limit': '0.8925', 'low_limit': ‘0.8075’} | 2 | 124 | 2F/124T FR:1.61% | SN: C0781060056JRD54Y, Config: Main 7-U-BTR,AAB fail, Sent to EE for verification1. The log shows: actual value is 0.0, {'high_limit': '0.8925', 'low_limit': ‘0.8075’}2. Visual inspection with microscope, found the test point covered by glue as attached pic.3. Clean the test point and retest pass 4. 3/14, add 1x the same failure, C078106007MJRD54B | 38376098/38430187
6 | IAXXX | FCT | HW |  | 2018-03-13 | 003/slot3 | MAC EFI USBC TA TB TOP ELOAD/MEASURE TA VCONN VOLTAGE 0.1A@EXT0015actual value is 0.003, {'high_limit': '5.5', 'low_limit': ‘4.5'} | 1 | 124 | 1F/124T RR:0.81% | SN: C0781060066JRD54V, Config: Main 7-U-BTR, AAB pass 1. The log shows: actual value is 0.003, {'high_limit': '5.5', 'low_limit': ‘4.5'} 2. Keep monitor. | 38410092
7 | IAXXX | FCT | HW |  | 2018-03-14 | 002/slot1 | IBOOT ACTIVE GROUP/DMM PPVBUS_USBC_XB actual value is 0.454, {'high_limit': '0.1', 'low_limit': '-0.1'} | 1 | 124 | 1F/124T FR:0.81% | SN: C078106005CJRD54S, Config: Main 7-U-BTR AAB fail, send to EE for FA | 38420256
8 | IAXXX | FCT | SW |  | 2018-03-14 | 005/slot1 | MAC EFI USBC TA TB TOP ELOAD/MEASURE TB VBUS VOLTAGE @3A@EXT0040 actual value is 2.75, {'high_limit': '5.5', 'low_limit': '4.5'} | 1 | 124 | 1R/124T RR:0.81% | SN: C078106006TJRD548, Config: Main 7-U-BTR, Fixture/Slot: 5/1,AA passSN: C0781150002JRG942, Fixture/Slot: 1/3, AAB pass Suspect 2.85A is the boundary current for the TOP TB VBUS.Need more data to identify whether this Eload current is suitable. Keep monitor.3/18, add 1x retest | 38451702
9 | IAXXX | FCT | TBD |  | 2018-03-14 | 001/slot2 | MAC EFI USBC TA TB TOP ELOAD/MEASURE TA VBUS VOLTAGE @1A@EXT0013 actual value is 0.0, {'high_limit': '5.5', 'low_limit': '4.5'} | 1 | 124 | 1R/124T RR:0.81% | SN: C0781060053JRD541, Config: Main 7-U-BTR, Fixture/Slot: 1/2 AA pass Keep monitor. | 38451754
10 | IAXXX | FCT | TBD |  | 2018-03-14 | 002/slot1 | MAC EFI USBC TA TB TOP ELOAD/MEASURE TB VCONN CURRENT OCP actual value is 619.287, {'high_limit': '600', 'low_limit': '-0.1'} | 1 | 124 | 1R/124T RR:0.81% | SN: C078112000JJKL26J, Config: Main 2-B-BTR, Fixture/Slot: 2/1 AA pass Keep monitor. | 38451819
11 | IAXXX | FCT | HW |  | 2018-03-14 | 002/slot1 | IBOOT ACTIVE GROUP/DMM PP0V9_SSD0 actual value is 0.0, {'high_limit': '0.99', 'low_limit': '0.81'} | 1 | 124 | 1R/124T RR:0.81% | SN: C078106007NJRD54A, Config: Main 7-U-BTR, Fixture/Slot: 2/1AA passSN: C0781160015JHV26Z, Fixture/Slot: 5/2, AA pass 1, We check the TP under microscope, and it’s OK. 2, Take the blue tape for this TP. Result is OK. 3, Suspect contact issue. Keep monitor.4, 3/19, add 1x retest | 38451866
12 | IAXXX | FCT | TBD |  | 2018-03-14 | 003/slot2 | iEFI SOC GROUP/READ ALL TEMP@SOC0052 Timed out | 3 | 124 | 1R/124T RR:0.81% | SN: C078106006VJRD546, Config: Main 7-U-BTR, Fixture/Slot: 3/2, AA passSN: C078115002UJRWL3N, Main 65-U CTO , Fixture/Slot: 6/2, AA passSN: C078117000SJRVW4J, Fixture/Slot: 3/1, AA pass 1, The response of DUT is abnormal after sending the cmd. But becoming normal when retest. 2, Keep monitor.3, 3/17, add 1x retest4, 3/20, add 1x retest | 38451912

## Dry-Run Loop Test Report
IAXXX FCT P1 Dry Run Loop Test Report
SW Bundle Version: iOS Bundle: iEFI Version: EFI Version: IA OVL Version: 1.0.1 AP Python Version: 2.12.6
Update: 2018/02/09 D |  |  |  | No issue, validated pass
Validation MLB: P1 |  |  |  | Root caused issue, low risk for build
Issue not root caused,critical for build
Issue impact input or shipping, blocker for build
Date | Input Loop Datas | PASS Count | FAIL Count | Retest Rate | DUT SN | DFU Bundle Version | Config Numbers | Slot | Fail Group | Fail Comment | Fail Analysis | IA DRI | NAPA DRI | Status | Remark
20180201N | 146 | 76 | 70 | 47.95% | C077494000JJJ3N8J | 4K52a | 12 Main 272A | 1 | IBOOT GROUP | Iboot powersequence delay issue; | 1 FAIL Need more delay for config power sequence. | Ray.huang |  | Closed
[9 empty] | iEFI SOC GROUP | Read SOC temperature command; | 1 FAIL at read SOC temp command. Diags command random fail. Need NAPA help to loop at this command stability. | Ray.huang |  | Closed | 1, Waiting for NAPA verify diags command: temp —all. 20180126 2, Skip this command error message. Will use PASS instead. Just for correct data. Confirm with David. 20180206
[10 empty] | Diags command timeout issue | 1 FAIL Need more delay for waiting DUT output signal response data. | Ray.huang |  | Closed | 1, Divide loopaudio command to send and detect. Diags will random timeout for this command.
[9 empty] | USBC ELOAD | USBC config delay issue; | 2 FAIL Need more delay wait for TYPE-C test module configure. | Ray.huang |  | Closed
[5 empty] | C0774940007JJ3N8V | 4K52 | 7 Main 272A | 0 | iEFI SOC GROUP | Read SOC temperature command; | 1 FAIL at read SOC temp command. Diags command random fail. Need NAPA help to loop at this command stability. | Ray.huang |  | Closed | 1, Waiting for NAPA verify diags command: temp —all. 20180126 2, Skip this command error message. Will use PASS instead. Just for correct data. Confirm with David. 20180206
[10 empty] | Enter Diags FAIL | 1 FAIL at DUT power on and the boot to re coverage mode. Log show DUT panic. | Ray.huang |  | Closed | 1, Keep monitoring. 20180202
[10 empty] | Diags command timeout issue | 1 FAIL Need more delay for waiting DUT output signal response data. | Ray.huang |  | Closed | 1, Divide loopaudio command to send and detect. Diags will random timeout for this command.
[9 empty] | USBC ELOAD | USBC config delay issue; | 2 FAIL Need more delay wait for TYPE-C test module configure. | Ray.huang |  | Closed
[5 empty] | C0774940001JJ3N81 | 4K52a | NA | 2 | IEFI AUDIO MIKEY | Mikey tone function; Mikey detect MIC and headphone function; | 48 FAIL at Mikey function test; | Ray.huang |  | Closed | 1, Need to confirm if DFU bundle issue or DUT hardware issue. 2, Re-do the DFU, 81SN DUT also fail at the Mikey test items. 20180202
[9 empty] | iEFI SOC GROUP | Read SOC temperature command; | 1 FAIL at read SOC temp command. Diags command random fail. Need NAPA help to loop at this command stability. | Ray.huang |  | Closed | 1, Waiting for NAPA verify diags command: temp —all. 20180126 2, Skip this command error message. Will use PASS instead. Just for correct data. Confirm with David. 20180206
20180202N | 87 | 65 | 22 | 25.29% | C077494000JJJ3N8J | 4K52a | 12 Main 272A | 0 | iEFI SOC GROUP | Read SOC temperature command; | 1 FAIL at read SOC temp command. Diags command random fail. Need NAPA help to loop at this command stability. | Ray.huang |  | Closed | 1, Waiting for NAPA verify diags command: temp —all. 20180126 2, Skip this command error message. Will use PASS instead. Just for correct data. Confirm with David. 20180206
[9 empty] | IEFI AUDIO MIKEY TONES | DUT DETECT TONE 0X00 | 1 FAIL at Mikey function test; Add delay for DUT Mikey config and then loop 80datas, issue has gone. Keep monitoring. | Ray.huang |  | Closed | 1, Keep monitoring for new test sequence, check Mikey stability. 20180203
[5 empty] | C077494000NJJ3N8E | 4K52a | 6 Main 272A | 1 | iEFI SOC GROUP | Read SOC temperature command; | 1 FAIL at read SOC temp command. Diags command random fail. Need NAPA help to loop at this command stability. | Ray.huang |  | Closed | 1, Waiting for NAPA verify diags command: temp —all. 20180126 2, Skip this command error message. Will use PASS instead. Just for correct data. Confirm with David. 20180206
[9 empty] | IEFI AUDIO MIKEY TONES | DUT DETECT TONE 0X00 | 1 FAIL at Mikey function test; Add delay for DUT Mikey config and then loop 80datas, issue has gone. Keep monitoring. | Ray.huang |  | Closed | 1, Keep monitoring for new test sequence, check Mikey stability. 20180203
[5 empty] | C0774940007JJ3N8V | 4K52b | 7 Main 272A | 2 | IEFI AUDIO HEADSET CHINA RTOL XTALK | DETECT OUTPUT 1K TONE FINISHED | 3 FAIL at loop audio headset command. Didn’t see DUT response. Re-do new DFU, check this issue if happen again. | Ray.huang |  | Closed | 1, Will keep looping this test group data. Also check this issue if test-plan issue or DUT bundle issue. 20180203 2, Change loop audio test sequence, add delay wait for :-), Loop more then 100 datas, do not see this issue again. 20180206
[9 empty] | IEFI AUDIO MIKEY TONES | DUT DETECT TONE 0X00 | 3 FAIL at Mikey function test; Add delay for DUT Mikey config and then loop 80datas, issue has gone. Keep monitoring. | Ray.huang |  | Closed | 1, Keep monitoring for new test sequence, check Mikey stability. 20180203
[9 empty] | iEFI SOC GROUP | Read SOC temperature command; | 1 FAIL at read SOC temp command. Diags command random fail. Need NAPA help to loop at this command stability. | Ray.huang |  | Closed | 1, Waiting for NAPA verify diags command: temp —all. 20180126 2, Skip this command error message. Will use PASS instead. Just for correct data. Confirm with David. 20180206
20180203-04 | 2120 | 2073 | 47 | 2.217% | C077494000JJJ3N8J | 4K52a | 12 Main 272A | 0 | iEFI SOC GROUP | Read SOC temperature command; | 1 FAIL at read SOC temp command. Diags command random fail. Need NAPA help to loop at this command stability. | Ray.huang |  | Closed | 1, Waiting for NAPA verify diags command: temp —all. 20180126 2, Skip this command error message. Will use PASS instead. Just for correct data. Confirm with David. 20180206
[9 empty] | IEFI AUDIO HEADSET CHINA RTOL XTALK | DETECT OUTPUT 1K TONE FINISHED | 5 FAIL at loop audio headset command. Didn’t see DUT response. Re-do new DFU, check this issue if happen again. | Ray.huang |  | Closed | 1, Loop test at 20180203-04. Found the TOP1 issue is Headset reset. Will continue looking on this fail. Need more DATA. 20180205 2, Change loop audio test sequence, add delay wait for :-), Loop more then 100 datas, do not see this issue again. 20180206
[5 empty] | C0774940007JJ3N8V | 4K52b | 7 Main 272A | 1 | iEFI SOC GROUP | Read SOC temperature command; | 1 FAIL at read SOC temp command. Diags command random fail. Need NAPA help to loop at this command stability. | Ray.huang |  | Closed | 1, Waiting for NAPA verify diags command: temp —all. 20180126 2, Skip this command error message. Will use PASS instead. Just for correct data. Confirm with David. 20180206
[9 empty] | IEFI AUDIO HEADSET CHINA RTOL XTALK | DETECT OUTPUT 1K TONE FINISHED | 7 FAIL at loop audio headset command. Didn’t see DUT response. Re-do new DFU, check this issue if happen again. | Ray.huang |  | Closed | 1, Loop test at 20180203-04. Found the TOP1 issue is Headset reset. Will continue looking on this fail. Need more DATA. 20180205 2, Change loop audio test sequence, add delay wait for :-), Loop more then 100 datas, do not see this issue again. 20180206
[5 empty] | C077494000NJJ3N8E | 4K52a | 6 Main 272A | 2 | iEFI SOC GROUP | Read SOC temperature command; | 1 FAIL at read SOC temp command. Diags command random fail. Need NAPA help to loop at this command stability. | Ray.huang |  | Closed | 1, Waiting for NAPA verify diags command: temp —all. 20180126 2, Skip this command error message. Will use PASS instead. Just for correct data. Confirm with David. 20180206
[9 empty] | IEFI AUDIO HEADSET CHINA RTOL XTALK | DETECT OUTPUT 1K TONE FINISHED | 8 FAIL at loop audio headset command. Didn’t see DUT response. Re-do new DFU, check this issue if happen again. | Ray.huang |  | Closed | 1, Loop test at 20180203-04. Found the TOP1 issue is Headset reset. Will continue looking on this fail. Need more DATA. 20180205 2, Change loop audio test sequence, add delay wait for :-), Loop more then 100 datas, do not see this issue again. 20180206
20180205 | 81 | 75 | 6 | 7.407% | C0774940007JJ3N8V | shasta_gibraltar4k_4K57 | 7 Main 272A | 0 | NA | NA | NA |  |  | NA
[5 empty] | C077494000NJJ3N8E | casaval_gibraltar4k_4K52a | 6 Main 272A | 1 | iEFI SOC GROUP | Read SOC temperature command; | 1 FAIL at read SOC temp command. Diags command random fail. Need NAPA help to loop at this command stability. | Ray.huang |  | Closed | 1, Waiting for NAPA verify diags command: temp —all. 20180126 2, Skip this command error message. Will use PASS instead. Just for correct data. Confirm with David. 20180206
[9 empty] | MAC EFI BOOT | WAIT MOJO PROMPT | 1 FAIL From the test log, looks like TM missing the power on moment data. So need open PCH before boot MAC EFI. | Ray.huang | 37296514 | Closed | 1, From the log, looks like receive data is too late by boot MAC EFI. Need re-verify open PCH timing for boot MAC EFI. 20180206 2, Open PCH before MAC EFI boot. Keep monitoring new test sequence. 20180206N
[5 empty] | C077494000JJJ3N8J | shasta_gibraltar4k_4K57 | 12 Main 272A | 2 | iEFI SOC GROUP | Read SOC temperature command; | 1 FAIL at read SOC temp command. Diags command random fail. Need NAPA help to loop at this command stability. | Ray.huang |  | Closed | 1, Waiting for NAPA verify diags command: temp —all. 20180126 2, Skip this command error message. Will use PASS instead. Just for correct data. Confirm with David. 20180206
[9 empty] | MAC EFI BOOT | WAIT MOJO PROMPT | 1 FAIL From the test log, looks like TM missing the power on moment data. So need open PCH before boot MAC EFI. | Ray.huang | 37296514 | Closed | 1, From the log, looks like receive data is too late by boot MAC EFI. Need re-verify open PCH timing for boot MAC EFI. 20180206 2, Open PCH before MAC EFI boot. Keep monitoring new test sequence. 20180206N
20180206 | 205 | 189 | 16 | 7.805% | C077494000AJJ3N8S | casaval_gibraltar4k_4K52b | 20 Main 272A | 0 | CB ERROR | RTC SET | 1 FAIL From the test log, DUT didn’t response rct set command. Need keep monitoring on this failure. | Ray.huang |  | Closed | 1, Keep monitoring. 20180206 2,Only one random fail at total 250 datas. Keep monitoring. 20180208
[9 empty] | IBOOT GROUP | ENTER IBOOT | 2 FAIL DUT no response data at IBOOT mode. Also for the error command “chekcbootstatus”, DUT do not response anything. Need keep monitoring this failure, check stability. | Ray.huang |  | Closed | 1, Need more DUT data on this DFU bundle. Will change another DUT to check this issue. 20180207 2, More then 250 looping datas, do not saw this issue. Will keep monitoring. 20180208
[9 empty] | IEFI AUDIO MIKEY TONES | Mikey tone function | 3 FAIL DUT response china mode Mikey but do not response global mode Mikey. | Ray.huang |  | Closed | 1. Need more data on others DUT. For the 4K57 bundle loop, do not found this issue again. 20180207 2, Two fail at total 250 loop data. Need more data to check this function stability. 20180208 3, Random happened this issue at 200 loop datas. Need signal shielding for Mikey circuit. Will add this change for P1 build fixture. Also when switch Mikey circuit for DUT, have not setup delay for this timing at test-plan. Will add delay for this issue. 20180209
[9 empty] | IBOOT GROUP | POWER SEQUENCE STOP | 2 FAIL Need set timeout for power sequence for close API timing. | Ray.huang |  | Closed | 1, Will add timeout setup at test-plan for this item. Keep monitoring. 20180207
[5 empty] | C0774940003JJ3N8Z | casaval_gibraltar4k_4K52b | 1 Main 272A | 1 | IBOOT GROUP | ENTER IBOOT | 1 FAIL DUT no response data at IBOOT mode. Also for the error command “chekcbootstatus”, DUT do not response anything. Need keep monitoring this failure, check stability. | Ray.huang |  | Closed | 1, Need more DUT data on this DFU bundle. Will change another DUT to check this issue. 20180207 2, More then 250 looping datas, do not saw this issue. Will keep monitoring. 20180208
[9 empty] | IEFI AUDIO HEADSET CHINA RTOL XTALK | PARSE HP_L_CH_DMIC_THDN | 2 FAIL Normal measurement limit is -40 to -100. Measurement is -37dB. Need put out the raw data to analysis this issue. Need diags team help to debug this random bug. | Ray.huang |  | Ongoing | 1, Need NAPA help to analysis this issue. 20180207 2, Two fail at total 250 loop data. Need more data to check this function stability. 20180208 3, Need to put out the raw data of audio waveform. Also can delete 5000 data when start to loopback audio. J137 project have delete 5000 sample datas at the beginning. Wave the waveform unstable issue. 20180209
[9 empty] | IBOOT GROUP | POWER SEQUENCE STOP | 2 FAIL Need set timeout for power sequence for close API timing. | Ray.huang |  | Closed | 1, Will add timeout setup at test-plan for this item. Keep monitoring. 20180207
[5 empty] | C0774940005JJ3N8X | casaval_gibraltar4k_4K52b | 3 Main 272A | 2 | MAC EFI POWER OFF | WAIT FOR INTEL OFF | 1 FAIL DUT power rail didn’t down by the command “reset -s”. Need keep monitoring on this failure. | Ray.huang |  | Closed | 1, Keep monitoring. 20180207 2,Only one random fail at total 250 datas. Keep monitoring. 20180208
[9 empty] | IBOOT GROUP | POWER SEQUENCE STOP | 2 FAIL Need set timeout for power sequence for close API timing. | Ray.huang |  | Closed | 1, Will add timeout setup at test-plan for this item. Keep monitoring. 20180207
20180207N | 255 | 249 | 6 | 2.353% | C0774940005JJ3N8X | casaval_gibraltar4k_4K52b | 3 Main 272A | 0 | MAC EFI POWER OFF | WAIT FOR INTEL OFF | 1 FAIL DUT power rail didn’t down by the command “reset -s”. Need keep monitoring on this failure. | Ray.huang |  | Closed | 1,Only one random fail at total 250 datas. Keep monitoring. 20180208
[5 empty] | C077494000AJJ3N8S | casaval_gibraltar4k_4K52b | 20 Main 272A | 1 | IEFI AUDIO MIKEY TONES | Mikey tone function | 2 FAIL DUT response china mode Mikey but do not response global mode Mikey. | Ray.huang |  | Closed | 1, Two fail at total 250 loop data. Need more data to check this function stability. 20180208 2, Random happened this issue at 200 loop datas. Need signal shielding for Mikey circuit. Will add this change for P1 build fixture. Also when switch Mikey circuit for DUT, have not setup delay for this timing at test-plan. Will add delay for this issue. 20180209
[5 empty] | C0774940003JJ3N8Z | casaval_gibraltar4k_4K52b | 1 Main 272A | 2 | CB ERROR | RTC SET | 1 FAIL From the test log, DUT didn’t response rct set command. Need keep monitoring on this failure. | Ray.huang |  | Closed | 1,Only one random fail at total 250 datas. Keep monitoring. 20180208
[9 empty] | IEFI AUDIO HEADSET CHINA RTOL XTALK | PARSE HP_L_CH_DMIC_THDN | 2 FAIL Normal measurement limit is -40 to -100. Measurement is -37dB. Need put out the raw data to analysis this issue. Need diags team help to debug this random bug. | Ray.huang |  | Ongoing | 1, Need to put out the raw data of audio waveform. Also can delete 5000 data when start to loopback audio. J137 project have delete 5000 sample datas at the beginning. Skip the waveform unstable at beginning line issue. 20180209
20180208N | 218 | 212 | 6 | 2.752% | C0774940005JJ3N8X | casaval_gibraltar4k_4K52b | 3 Main 272A | 0 | IEFI AUDIO HEADSET CHINA RTOL XTALK | PARSE HP_L_CH_DMIC_THDN | 2 FAIL Normal measurement limit is -40 to -100. Measurement is -37dB. Need put out the raw data to analysis this issue. Need diags team help to debug this random bug. | Ray.huang |  | Ongoing | 1, Need to put out the raw data of audio waveform. Also can delete 5000 data when start to loopback audio. J137 project have delete 5000 sample datas at the beginning. Skip the waveform unstable at beginning line issue. 20180209
[5 empty] | C077494000AJJ3N8S | casaval_gibraltar4k_4K52b | 20 Main 272A | 1 | MAC EFI BOOT | WAIT MOJO PROMPT | 1 FAIL DUT response data but can boot to MAC EFI. The MAC EFI power rail didn’t output. So DUT hung at booting to MAC EFI. | Ray.huang |  | Closed | 1, DUT response data but can’t boot to mac EFI. Seems like EFI status is not stable. Wait for \;> timeout. Need keep monitoring on this issue. Check if new DFU bundle can fix this random issue. 20180209
[5 empty] | C0774940003JJ3N8Z | casaval_gibraltar4k_4K52b | 1 Main 272A | 2 | IEFI AUDIO MIKEY TONES | Mikey tone function | 1 FAIL DUT response china mode Mikey but do not response global mode Mikey. | Ray.huang |  | Closed | 1, Random happened this issue at 200 loop datas. Need signal shielding for Mikey circuit. Will add this change for P1 build fixture. Also when switch Mikey circuit for DUT, have not setup delay for this timing at test-plan. Will add delay for this issue. 20180209
[9 empty] | MAC EFI BOOT | WAIT MOJO PROMPT | 1 FAIL DUT response data but can boot to MAC EFI. The MAC EFI power rail didn’t output. So DUT hung at booting to MAC EFI. | Ray.huang |  | Closed | 1, DUT response data but can’t boot to mac EFI. Seems like EFI status is not stable. Wait for \;> timeout. Need keep monitoring on this issue. Check if new DFU bundle can fix this random issue. 20180209
[9 empty] | IEFI AUDIO HEADSET CHINA RTOL XTALK | PARSE HP_L_CH_DMIC_THDN | 1 FAIL Normal measurement limit is -40 to -100. Measurement is -37dB. Need put out the raw data to analysis this issue. Need diags team help to debug this random bug. | Ray.huang |  | Ongoing | 1, Need to put out the raw data of audio waveform. Also can delete 5000 data when start to loopback audio. J137 project have delete 5000 sample datas at the beginning. Skip the waveform unstable at beginning line issue. 20180209